## Executive Summary
SharePoint Online Cross-Tenant Migration — Project Plan
Source Tenant | hawaiianair.sharepoint.com
Target Tenant | alaskaair.sharepoint.com
Deadline | May 30, 2026
Prepared | March 17, 2026
Generated | March 18, 2026 15:10
Site Comparison
Item | In-Flight Services (IFS) | Flight Operations
Source URL | /sites/ifs | /sites/flightoperations
Site Template | Communication Site | Communication Site
Language | English US (1033) | English US (1033)
Created (source) | August 26, 2018 | June 11, 2020
Export Size | 1,369.9 MB | 108.8 MB
Lists / Libraries | 122 (103 visible) | 32 (14 visible)
Pages (SitePages) | 356 | 20 + 27 in library
Documents to migrate | ~1,272 files | ~81 files
Content Types | 65 | 65
Site Columns | 166 | Standard only

## Project Plan
ID | Phase | Task | Site | Owner | Start Date | End Date | Duration (Days) | Status | % Complete | Notes/Dependencies
1 | PREP | Confirm Alaska Air tenant admin URL | BOTH | IT Admin | 2026-03-17 | 2026-03-19 | 2 | Not Started | 0%
2 | PREP | Confirm PnP PowerShell version (UseWebLogin vs Interactive) | BOTH | Engineer | 2026-03-17 | 2026-03-19 | 2 | Not Started | 0%
3 | PREP | Identify/create migration service account | BOTH | IT Admin | 2026-03-18 | 2026-03-21 | 3 | Not Started | 0%
4 | PREP | Export Term Store terms from hawaiianair tenant | BOTH | Engineer | 2026-03-18 | 2026-03-21 | 3 | Not Started | 0%
5 | PREP | DECISION: Re-populate high-volume list data? (FlightSchedules 12,950; Deadhead 599; PBS Archives ~2,200+; Events 483) | IFS | Stakeholder | 2026-03-17 | 2026-03-24 | 5 | Not Started | 0% | Decision required by Mar 24
6 | PREP | DECISION: Re-populate FlightOps list data? (Daily Flight Schedules 4,471; Instructor/Evaluator/LCA 141) | FlightOps | Stakeholder | 2026-03-17 | 2026-03-24 | 5 | Not Started | 0% | Decision required by Mar 24
7 | PREP | Identify all Power Automate flows on both sites | BOTH | BA/Owner | 2026-03-18 | 2026-03-24 | 5 | Not Started | 0%
8 | PREP | Identify AAD groups/users needed in target | BOTH | IT Admin | 2026-03-18 | 2026-03-24 | 5 | Not Started | 0%
9 | Week 1-2: Site Creation & Initial Build | [IFS] Create Communication Site in target tenant | IFS | IT Admin | 2026-03-24 | 2026-03-24 | 1 | Not Started | 0%
10 | Week 1-2: Site Creation & Initial Build | [IFS] Run Build-IFSSite.ps1 — applies template, creates 103 lists/libraries, sets navigation | IFS | Engineer | 2026-03-25 | 2026-03-26 | 2 | Not Started | 0% | Depends on Task 9
11 | Week 1-2: Site Creation & Initial Build | [IFS] Verify site is up, Home page loads, Quick Launch visible | IFS | Engineer | 2026-03-26 | 2026-03-26 | 1 | Not Started | 0% | Depends on Task 10
12 | Week 1-2: Site Creation & Initial Build | [FlightOps] Create Communication Site | FlightOps | IT Admin | 2026-03-24 | 2026-03-24 | 1 | Not Started | 0%
13 | Week 1-2: Site Creation & Initial Build | [FlightOps] IMMEDIATELY verify Crew Planning section exists — DAY-ONE PRIORITY (/sites/flightoperations/CrewPlanning) | FlightOps | Engineer | 2026-03-24 | 2026-03-24 | 1 | Not Started | 0% | ⚠ DAY-ONE PRIORITY — must be verified same day as site creation
14 | Week 1-2: Site Creation & Initial Build | [FlightOps] Run Build-FlightOpsSite.ps1 — applies template, creates 14 lists, sets nav | FlightOps | Engineer | 2026-03-25 | 2026-03-26 | 2 | Not Started | 0% | Depends on Task 12
15 | Week 1-2: Site Creation & Initial Build | [FlightOps] Verify all 7 Top Nav nodes resolve (Home, On the Line, Crew Planning, Publications, Training, Forms, Admin) | FlightOps | Engineer | 2026-03-26 | 2026-03-26 | 1 | Not Started | 0% | Depends on Task 14
16 | Week 1-2: Site Creation & Initial Build | [IFS] Upload documents (1,272 files / 1.37 GB) — run off-peak hours | IFS | Engineer | 2026-03-27 | 2026-04-02 | 5 | Not Started | 0% | Off-peak upload; PnP throttle retry
17 | Week 1-2: Site Creation & Initial Build | [FlightOps] Upload documents (81 files) | FlightOps | Engineer | 2026-03-27 | 2026-03-28 | 1 | Not Started | 0%
18 | Week 1-2: Site Creation & Initial Build | [FlightOps] Verify Crew Planning page content loaded correctly from template | FlightOps | Content | 2026-03-30 | 2026-03-31 | 2 | Not Started | 0%
19 | Week 1-2: Site Creation & Initial Build | [FlightOps] Verify EFB page renders | FlightOps | Content | 2026-03-30 | 2026-03-30 | 1 | Not Started | 0%
20 | Week 3-4: Page Fixes, Navigation & Flows | [IFS] Page review — all 356 pages, fix broken web parts (person, news, list rollup) | IFS | Content | 2026-04-02 | 2026-04-14 | 10 | Not Started | 0%
21 | Week 3-4: Page Fixes, Navigation & Flows | [IFS] Verify and fix all 31 Quick Launch nodes | IFS | Engineer | 2026-04-03 | 2026-04-05 | 2 | Not Started | 0%
22 | Week 3-4: Page Fixes, Navigation & Flows | [IFS] Verify Top Nav (Forms link) | IFS | Engineer | 2026-04-03 | 2026-04-03 | 1 | Not Started | 0%
23 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] Page review — all 47 pages | FlightOps | Content | 2026-04-02 | 2026-04-10 | 7 | Not Started | 0%
24 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] Crew Planning — deep content review, verify all linked pages under /CrewPlanning | FlightOps | Content | 2026-04-02 | 2026-04-07 | 4 | Not Started | 0%
25 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] Verify and fix all 8 Quick Launch nodes | FlightOps | Engineer | 2026-04-03 | 2026-04-04 | 2 | Not Started | 0%
26 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] Verify all 7 Top Nav nodes | FlightOps | Engineer | 2026-04-03 | 2026-04-04 | 2 | Not Started | 0%
27 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] On the Line (/otl) section review | FlightOps | Content | 2026-04-05 | 2026-04-08 | 3 | Not Started | 0%
28 | Week 3-4: Page Fixes, Navigation & Flows | [FlightOps] Training section review | FlightOps | Content | 2026-04-08 | 2026-04-10 | 3 | Not Started | 0%
29 | Week 3-4: Page Fixes, Navigation & Flows | Re-create Term Store terms (from PREP export) | BOTH | Engineer | 2026-04-02 | 2026-04-09 | 5 | Not Started | 0% | Depends on Task 4
30 | Week 3-4: Page Fixes, Navigation & Flows | Rebuild Power Automate flows (GAP-04) | BOTH | Engineer | 2026-04-07 | 2026-04-18 | 10 | Not Started | 0% | Depends on Task 7
31 | Week 5-6: Permissions, Data & URL Fixes | [IFS] Assign permissions — owners, members, visitors groups from Alaska Air AAD | IFS | IT Admin | 2026-04-14 | 2026-04-17 | 3 | Not Started | 0%
32 | Week 5-6: Permissions, Data & URL Fixes | [FlightOps] Assign permissions | FlightOps | IT Admin | 2026-04-14 | 2026-04-17 | 3 | Not Started | 0%
33 | Week 5-6: Permissions, Data & URL Fixes | [IFS] Re-populate high-volume lists (if approved) — FlightSchedules, Deadhead Booking, PBS Archives | IFS | Data/BA | 2026-04-14 | 2026-04-30 | 12 | Not Started | 0% | Depends on Task 5 decision
34 | Week 5-6: Permissions, Data & URL Fixes | [FlightOps] Re-populate lists (if approved) — Daily Flight Schedules, Instructor/Evaluator | FlightOps | Data/BA | 2026-04-14 | 2026-04-25 | 8 | Not Started | 0% | Depends on Task 6 decision
35 | Week 5-6: Permissions, Data & URL Fixes | Update embedded URLs / CDN refs in all pages | BOTH | Content | 2026-04-17 | 2026-04-24 | 5 | Not Started | 0%
36 | Week 5-6: Permissions, Data & URL Fixes | Fix person columns / user @domain references | BOTH | IT Admin | 2026-04-17 | 2026-04-24 | 5 | Not Started | 0% | Depends on Task 8
37 | Week 5-6: Permissions, Data & URL Fixes | Re-upload / re-link FlightOps video content (85 videos in Stream/SharePoint) | FlightOps | Content | 2026-04-17 | 2026-04-25 | 7 | Not Started | 0% | GAP-06
38 | Week 7-8: UAT | [IFS] UAT round 1 — content owners test all pages, lists, navigation, search | IFS | Stakeholder | 2026-04-28 | 2026-05-05 | 6 | Not Started | 0%
39 | Week 7-8: UAT | [FlightOps] UAT round 1 — pilots and crew mgmt test Crew Planning, OTL, Training, EFB, Daily Flight Schedules, Forms | FlightOps | Stakeholder | 2026-04-28 | 2026-05-05 | 6 | Not Started | 0%
40 | Week 7-8: UAT | [IFS] UAT defect fixes | IFS | Engineer | 2026-05-04 | 2026-05-12 | 7 | Not Started | 0%
41 | Week 7-8: UAT | [FlightOps] UAT defect fixes | FlightOps | Engineer | 2026-05-04 | 2026-05-12 | 7 | Not Started | 0%
42 | Week 7-8: UAT | [IFS] UAT round 2 — sign-off test pass | IFS | Stakeholder | 2026-05-09 | 2026-05-14 | 4 | Not Started | 0%
43 | Week 7-8: UAT | [FlightOps] UAT round 2 — sign-off test pass | FlightOps | Stakeholder | 2026-05-09 | 2026-05-14 | 4 | Not Started | 0%
44 | Week 9-10: Final Checks & Go-Live | Trigger search crawl on both sites | BOTH | IT Admin | 2026-05-12 | 2026-05-13 | 1 | Not Started | 0%
45 | Week 9-10: Final Checks & Go-Live | External integrations re-pointed (GAP-05) — FlightSchedules feed, Deadhead system | BOTH | IT/Dev | 2026-05-12 | 2026-05-20 | 6 | Not Started | 0% | GAP-05
46 | Week 9-10: Final Checks & Go-Live | Final content review — spot-check key pages | BOTH | Stakeholder | 2026-05-13 | 2026-05-20 | 5 | Not Started | 0%
47 | Week 9-10: Final Checks & Go-Live | Stakeholder sign-off received | BOTH | Stakeholder | 2026-05-20 | 2026-05-20 | 1 | Not Started | 0%
48 | Week 9-10: Final Checks & Go-Live | Go-live user communications sent | BOTH | Comms Lead | 2026-05-19 | 2026-05-22 | 3 | Not Started | 0%
49 | Week 9-10: Final Checks & Go-Live | [IFS] Site go-live — users redirected | IFS | IT Admin | 2026-05-26 | 2026-05-26 | 1 | Not Started | 0% | Depends on Task 47
50 | Week 9-10: Final Checks & Go-Live | [FlightOps] Site go-live — users redirected | FlightOps | IT Admin | 2026-05-27 | 2026-05-27 | 1 | Not Started | 0% | Depends on Task 47
51 | Week 9-10: Final Checks & Go-Live | Buffer / contingency for both sites | BOTH | All | 2026-05-27 | 2026-05-30 | 3 | Not Started | 0%

## Key Milestones
# | Milestone Date | Milestone Description | Status
1 | 2026-03-24 | Both sites created in target tenant | Not Started
2 | 2026-03-24 | Crew Planning verified accessible (FlightOps day-one check) | Not Started
3 | 2026-03-26 | Both build scripts completed — structure live | Not Started
4 | 2026-04-02 | All documents uploaded | Not Started
5 | 2026-04-10 | All pages reviewed, navigation verified on both sites | Not Started
6 | 2026-04-18 | Power Automate flows rebuilt | Not Started
7 | 2026-04-30 | Data re-population complete (if approved) | Not Started
8 | 2026-05-14 | UAT complete, all defects resolved | Not Started
9 | 2026-05-20 | Final sign-off from stakeholders | Not Started
10 | 2026-05-26 | IFS go-live | Not Started
11 | 2026-05-27 | Flight Operations go-live | Not Started
12 | 2026-05-30 | DEADLINE — both sites live in target tenant | Not Started

## IFS Libraries and Lists
# | Name | Type | Items | Priority/Decision | Migration Notes | Status
1 | Admin | Document Library | 26 | Migrate |  | Not Started
2 | Briefing Sheets | Document Library | 166 | Migrate |  | Not Started
3 | Cabin Seat Agreements | Document Library | 20 | Migrate |  | Not Started
4 | Catering and Service | Document Library | 51 | Migrate |  | Not Started
5 | Catering and Service Communication | Document Library | 55 | Migrate |  | Not Started
6 | Corporate Safety and Security | Document Library | 22 | Migrate |  | Not Started
7 | Credit Card | Document Library | 31 | Migrate |  | Not Started
8 | Crew Scheduling | Document Library | 81 | Migrate |  | Not Started
9 | Documents | Document Library | 25 | Migrate |  | Not Started
10 | FAQ | Document Library | 8 | Migrate |  | Not Started
11 | Graphics Library | Document Library | 167 | Migrate |  | Not Started
12 | IFP Communication | Document Library | 373 | Migrate |  | Not Started
13 | IFS Training - Practical Training | Document Library | 14 | Migrate |  | Not Started
14 | IFS Training - Recurrent Awards | Document Library | 304 | Migrate |  | Not Started
15 | Safety Communication | Document Library | 20 | Migrate |  | Not Started
16 | Safety Reporting Tool | Document Library | 2 | Migrate |  | Not Started
17 | Shared Documents | Document Library | 4 | Migrate |  | Not Started
18 | Uniform and Grooming | Document Library | 3 | Migrate |  | Not Started
19 | Vacation | Document Library | 24 | Migrate |  | Not Started
20 | 2023 P and V Awards | Custom List | 2056 | Migrate |  | Not Started
21 | FA Base Month 2023 for IFS | Custom List | 1788 | Migrate |  | Not Started
22 | FA Base Month 2024 | Custom List | 2188 | Migrate |  | Not Started
23 | FA Base Month 2024 v2 | Custom List | 2188 | Migrate |  | Not Started
24 | flying to/from | Custom List | 18 | Migrate |  | Not Started
25 | RC3 Door Openings and Closings Playlist | Custom List | 8 | Migrate |  | Not Started
26 | Revision Cycle 2 Playlist | Custom List | 3 | Migrate |  | Not Started
27 | Town Hall Questions | Custom List | 0 | Migrate |  | Not Started
28 | B2B Library | Custom List | 11 | Migrate |  | Not Started
29 | 17.N. Contractual Leave Archive 2019 | Archive List | 0 | Low priority |  | Not Started
30 | 17.N. Contractual Leave Archive 2020 | Archive List | 0 | Low priority |  | Not Started
31 | 17.N. Contractual Leave Archive 2021 | Archive List | 0 | Low priority |  | Not Started
32 | 17.N. Contractual Leave Archive 2022 | Archive List | 0 | Low priority |  | Not Started
33 | 17.N. Contractual Leave Archive 2023 | Archive List | 0 | Low priority |  | Not Started
34 | 17.N. Contractual Leave Archive 2024 | Archive List | 0 | Low priority |  | Not Started
35 | 17.N. Contractual Leave Archive 2025 | Archive List | 0 | Low priority |  | Not Started
36 | 17.N. Contractual Leave Archive 2026 | Archive List | 0 | Low priority |  | Not Started
37 | Low Time Flying Archive 2019 | Archive List | 0 | Low priority |  | Not Started
38 | Low Time Flying Archive 2020 | Archive List | 0 | Low priority |  | Not Started
39 | Low Time Flying Archive 2021 | Archive List | 0 | Low priority |  | Not Started
40 | Low Time Flying Archive 2022 | Archive List | 0 | Low priority |  | Not Started
41 | Low Time Flying Archive 2023 | Archive List | 0 | Low priority |  | Not Started
42 | Low Time Flying Archive 2024 | Archive List | 0 | Low priority |  | Not Started
43 | Low Time Flying Archive 2025 | Archive List | 0 | Low priority |  | Not Started
44 | Low Time Flying Archive 2026 | Archive List | 0 | Low priority |  | Not Started
45 | PBS Award Archive 2016 | Archive List | 0 | Low priority |  | Not Started
46 | PBS Award Archive 2017 | Archive List | 0 | Low priority |  | Not Started
47 | PBS Award Archive 2018 | Archive List | 0 | Low priority |  | Not Started
48 | PBS Award Archive 2019 | Archive List | 0 | Low priority |  | Not Started
49 | PBS Award Archive 2020 | Archive List | 0 | Low priority |  | Not Started
50 | PBS Award Archive 2021 | Archive List | 0 | Low priority |  | Not Started
51 | PBS Award Archive 2022 | Archive List | 0 | Low priority |  | Not Started
52 | PBS Award Archive 2023 | Archive List | 0 | Low priority |  | Not Started
53 | PBS Award Archive 2024 | Archive List | 0 | Low priority |  | Not Started
54 | PBS Award Archive 2025 | Archive List | 0 | Low priority |  | Not Started
55 | PBS Award Archive 2026 | Archive List | 0 | Low priority |  | Not Started
56 | Vacancy Bid Archive 2021 | Archive List | 0 | Low priority |  | Not Started
57 | Vacancy Bid Archive 2022 | Archive List | 0 | Low priority |  | Not Started
58 | Vacancy Bid Archive 2023 | Archive List | 0 | Low priority |  | Not Started
59 | Vacancy Bid Archive 2024 | Archive List | 0 | Low priority |  | Not Started
60 | Vacancy Bid Archive 2025 | Archive List | 0 | Low priority |  | Not Started
61 | Vacancy Bid Archive 2026 | Archive List | 0 | Low priority |  | Not Started
62 | Vacation Annual Bidding 2021 | Archive List | 0 | Low priority |  | Not Started
63 | Vacation Annual Bidding 2022 | Archive List | 0 | Low priority |  | Not Started
64 | Vacation Annual Bidding 2023 | Archive List | 0 | Low priority |  | Not Started
65 | Vacation Annual Bidding 2024 | Archive List | 0 | Low priority |  | Not Started
66 | Vacation Annual Bidding 2025 | Archive List | 0 | Low priority |  | Not Started
67 | Vacation Annual Bidding 2026 | Archive List | 0 | Low priority |  | Not Started
68 | Vacation (Bonus Days) | Archive List | 0 | Low priority |  | Not Started
69 | LOA | Archive List | 0 | Low priority |  | Not Started
70 | COVID LOA | Archive List | 0 | Low priority |  | Not Started
71 | FlightSchedules | High-Volume List | 12950 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
72 | Deadhead Booking | High-Volume List | 599 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
73 | IFP Communication list | High-Volume List | 373 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
74 | Events/Calendar | High-Volume List | 483 | Migrate |  | Not Started
75 | Random Acts of Aloha | High-Volume List | 492 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
76 | In-Flight Training Videos | High-Volume List | 197 | Migrate |  | Not Started
77 | Daily Briefings | High-Volume List | 106 | Migrate |  | Not Started

## FlightOps Libraries and Lists
# | Name | Type | Items | Priority/Decision | Migration Notes | Status
1 | Documents | Document Library | 8 | Migrate |  | Not Started
2 | Flight Operations Videos | Document Library | 85 | Migrate (GAP-06) | Re-upload to Stream/SharePoint target | Not Started
3 | KCM | Document Library | 5 | Migrate |  | Not Started
4 | Security | Document Library | 4 | Migrate |  | Not Started
5 | Shared Documents | Document Library | 0 | Migrate |  | Not Started
6 | Daily Flight Schedules | High-Volume List | 4471 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
7 | Demo-Daily Flight Schedules | Custom List | 560 | Migrate |  | Not Started
8 | Instructor/Evaluator/LCA | High-Volume List | 141 | DECISION REQUIRED | Re-populate from source or start fresh? | Decision Required
9 | Technical Pilot Application List | Custom List | 1 | Migrate |  | Not Started

## Risk Register
Risk ID | Risk Description | Likelihood | Impact | Risk Score | Mitigation | Owner | Status
RISK-01 | No tenant admin access to alaskaair.sharepoint.com | HIGH | HIGH | Critical | Escalate to Alaska Air IT Admin immediately. Build-IFSSite.ps1 works if admin creates sites manually and grants Site Collection Admin rights to engineer. | IT Admin | Open
RISK-02 | PnP template apply fails on target (pages/branding errors) | MEDIUM | MEDIUM | Medium | Script has 4 fallback handler exclusion attempts. List/library build runs independently and is not blocked by template failure. | Engineer | Open
RISK-03 | High-volume list data (FlightSchedules, PBS) not available | HIGH | HIGH | Critical | Decision needed by Mar 24. If re-population required, contract a data migration tool (ShareGate, Metalogix) or export CSV from source. | Stakeholder | Open
RISK-04 | Managed metadata / Term Store not set up in target tenant | MEDIUM | MEDIUM | Medium | Export terms from source using Export-PnPTermGroupToXml and import to target before applying templates. | Engineer | Open
RISK-05 | User accounts do not exist in target tenant AAD | HIGH | MEDIUM | High | Audit all person columns and web part references. Create/sync accounts before UAT starts. | IT Admin | Open
RISK-06 | External video embeds / Stream links broken | HIGH | MEDIUM | High | Re-upload videos to SharePoint/Stream in target tenant and update embed URLs. | Content | Open
RISK-07 | IFS export is 1.37 GB — upload may be slow / throttled | MEDIUM | LOW | Low | Run uploads during off-peak hours. Script handles throttling via PnP retry logic. | Engineer | Open

## Go-Live Checklist
# | Category | Checklist Item | Status | Tested By | Date Tested | Notes
1 | IFS | Home page loads without errors | Not Tested
2 | IFS | All 15 Quick Launch links resolve | Not Tested
3 | IFS | Bidding (PBS) page functional | Not Tested
4 | IFS | Daily Briefing visible and current | Not Tested
5 | IFS | Training page loads correctly | Not Tested
6 | IFS | FlightSchedules list accessible with correct columns | Not Tested
7 | IFS | Search returns results from site content | Not Tested
8 | IFS | "Contact Us" form works (if Power Automate flow rebuilt) | Not Tested
9 | IFS | Mobile view renders correctly | Not Tested
10 | IFS | Permissions confirmed (members can view not edit unless intended) | Not Tested
11 | Flight Operations | Home page loads without errors | Not Tested
12 | Flight Operations | EFB page loads | Not Tested
13 | Flight Operations | On the Line sub-site navigation works | Not Tested
14 | Flight Operations | Crew Planning section functional | Not Tested
15 | Flight Operations | Daily Flight Schedules list accessible | Not Tested
16 | Flight Operations | Instructor / Evaluator list accessible with correct columns | Not Tested
17 | Flight Operations | Top Navigation all 7 links resolve | Not Tested
18 | Flight Operations | Forms section functional | Not Tested
19 | Flight Operations | Search returns results | Not Tested
20 | Both Sites | No @hawaiianair.com user references visible in web parts | Not Tested
21 | Both Sites | No broken images on any key page | Not Tested
22 | Both Sites | SSL / HTTPS valid | Not Tested
23 | Both Sites | Site logos / branding updated to Alaska Air | Not Tested
24 | Both Sites | Power Automate flows tested end-to-end | Not Tested
25 | Both Sites | External integrations verified | Not Tested
26 | Both Sites | Stakeholder sign-off received | Not Tested

## Out of Scope and Gaps
GAP ID | Description | Impact | Decision/Action Required | Owner | Status
GAP-01 | List item data for high-volume lists not exported | HIGH | DECISION REQUIRED: re-populate from source or start fresh? | Stakeholder | Decision Required
GAP-02 | User profile data references old @hawaiianair.com accounts | MEDIUM | Re-map to @alaskaair.com accounts | IT Admin | Open
GAP-03 | Permissions not migrated, all security groups must be rebuilt | HIGH | Create all AAD groups/users in target before UAT | IT Admin | Open
GAP-04 | Power Automate / Logic Apps not captured in schema export | MEDIUM | Identify all flows; rebuild in target tenant | Engineer | Open
GAP-05 | External integrations need re-pointing | HIGH | Identify all integration endpoints; re-point to new site URLs | IT/Dev | Open
GAP-06 | Video content (85 items) likely reference broken Stream/embed URLs | MEDIUM | Re-upload videos and update embed URLs | Content | Open
GAP-07 | Taxonomy / Term Store — TaxCatchAll columns suggest managed metadata in use | MEDIUM | Export terms; import to target before applying templates | Engineer | Open

## Site Columns (IFS)
# | InternalName | Type | Notes | Created in Target?
1 | ComplianceAssetId | Text | Compliance asset identifier | Not Started
2 | IsFeatured | Boolean | Feature flag for content | Not Started
3 | TaskOutcome | OutcomeChoice | Task outcome field | Not Started
4 | TaxKeywordTaxHTField | Note | Taxonomy keyword hidden field | Not Started
5 | TaxCatchAll | LookupMulti | Managed metadata catch-all (hidden) | Not Started
6 | TaxCatchAllLabel | LookupMulti | Managed metadata label (hidden) | Not Started
7 | WSEnabled | Boolean | Web service enabled flag | Not Started
8 | WSPublishState | Integer | Web service publish state | Not Started
9 | MyEditor | User | Custom editor user field | Not Started
10 | ParentFolderId | Integer | Parent folder identifier | Not Started
11 | ParentID | Lookup | Parent item ID lookup | Not Started
12 | ParentItemEditor | User | Parent item editor user field | Not Started
13 | ParentItemID | Integer | Parent item integer ID | Not Started

## Navigation
# | Site | Nav Type | Node Name | URL | Verified?
1 | IFS | Quick Launch | Home | /sites/ifs | Not Started
2 | IFS | Quick Launch | NEWS | /sites/ifs/SitePages/News-Hub.aspx | Not Started
3 | IFS | Quick Launch | Daily Briefing | /sites/ifs/SitePages/Daily-Briefing.aspx | Not Started
4 | IFS | Quick Launch | Bidding (PBS) | /sites/ifs/SitePages/PBS-BIDDING.aspx | Not Started
5 | IFS | Quick Launch | Crew Scheduling | /sites/ifs/SitePages/Scheduling.aspx | Not Started
6 | IFS | Quick Launch | Catering and Service | /sites/ifs/SitePages/Catering-and-Service.aspx | Not Started
7 | IFS | Quick Launch | IFM Safety and Security | /sites/ifs/SitePages/IFM-Cabin-Safety.aspx | Not Started
8 | IFS | Quick Launch | Training | /sites/ifs/SitePages/The-NEW-Train.aspx | Not Started
9 | IFS | Quick Launch | IMD | /sites/ifs/SitePages/IMD.aspx | Not Started
10 | IFS | Quick Launch | Uniform and Grooming | /sites/ifs/SitePages/Uniform.aspx | Not Started
11 | IFS | Quick Launch | Forms | /sites/ifs/SitePages/Forms.aspx | Not Started
12 | IFS | Quick Launch | Crew Accommodations | /sites/ifs/SitePages/Destinations.aspx | Not Started
13 | IFS | Quick Launch | Wings of Wellness | /sites/ifs/SitePages/Flight-Attendant-Mental-Health.aspx | Not Started
14 | IFS | Quick Launch | Inflight Admin | /sites/ifs/SitePages/Admin.aspx | Not Started
15 | IFS | Quick Launch | Contact Us! | /sites/ifs/SitePages/Contact-Us!.aspx | Not Started
16 | IFS | Quick Launch | Other Links (header) |  | Not Started
17 | IFS | Quick Launch | PBS Archive 2016 | /sites/ifs/Lists/PBSArchive2016 | Not Started
18 | IFS | Quick Launch | PBS Archive 2017 | /sites/ifs/Lists/PBSArchive2017 | Not Started
19 | IFS | Quick Launch | PBS Archive 2018 | /sites/ifs/Lists/PBSArchive2018 | Not Started
20 | IFS | Quick Launch | PBS Archive 2019 | /sites/ifs/Lists/PBSArchive2019 | Not Started
21 | IFS | Quick Launch | PBS Archive 2020 | /sites/ifs/Lists/PBSArchive2020 | Not Started
22 | IFS | Quick Launch | PBS Archive 2021 | /sites/ifs/Lists/PBSArchive2021 | Not Started
23 | IFS | Quick Launch | PBS Archive 2022 | /sites/ifs/Lists/PBSArchive2022 | Not Started
24 | IFS | Quick Launch | PBS Archive 2023 | /sites/ifs/Lists/PBSArchive2023 | Not Started
25 | IFS | Quick Launch | Vacancy Bid 2021 | /sites/ifs/Lists/VacancyBid2021 | Not Started
26 | IFS | Quick Launch | Vacancy Bid 2022 | /sites/ifs/Lists/VacancyBid2022 | Not Started
27 | IFS | Quick Launch | Vacancy Bid 2023 | /sites/ifs/Lists/VacancyBid2023 | Not Started
28 | IFS | Quick Launch | LTF Archive | /sites/ifs/Lists/LTFArchive | Not Started
29 | IFS | Quick Launch | Vacation Archive | /sites/ifs/Lists/VacationArchive | Not Started
30 | IFS | Quick Launch | Leave Archive | /sites/ifs/Lists/LeaveArchive | Not Started
31 | IFS | Quick Launch | Recent (auto-node) |  | Not Started
32 | IFS | Top Navigation | Forms | /sites/ifs/Forms | Not Started
33 | FlightOps | Quick Launch | Home | /sites/flightoperations | Not Started
34 | FlightOps | Quick Launch | On the Line | /sites/flightoperations/otl | Not Started
35 | FlightOps | Quick Launch | Crew Planning | /sites/flightoperations/CrewPlanning | Not Started
36 | FlightOps | Quick Launch | Training | /sites/flightoperations/training | Not Started
37 | FlightOps | Quick Launch | Crew Accommodations | /sites/flightoperations/crewaccommodations | Not Started
38 | FlightOps | Quick Launch | EFB | /sites/flightoperations/SitePages/EFB.aspx | Not Started
39 | FlightOps | Quick Launch | Forms | /sites/flightoperations/forms | Not Started
40 | FlightOps | Quick Launch | Admin | /sites/flightoperations/admin | Not Started
41 | FlightOps | Top Navigation | Home | /sites/flightoperations | Not Started
42 | FlightOps | Top Navigation | On the Line | /sites/flightoperations/otl | Not Started
43 | FlightOps | Top Navigation | Crew Planning | /sites/flightoperations/CrewPlanning | Not Started
44 | FlightOps | Top Navigation | Publications | /sites/flightoperations/publications | Not Started
45 | FlightOps | Top Navigation | Training | /sites/flightoperations/training | Not Started
46 | FlightOps | Top Navigation | Forms | /sites/flightoperations/forms | Not Started
47 | FlightOps | Top Navigation | Admin | /sites/flightoperations/admin | Not Started